## Consultancy Services
[5 empty] | Contract Type |  |  |  | Preparation Term of Reference | [7 empty] | Short List |  |  |  | Request for Proposals / Bid |  |  |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiations (N) | [9 empty] | Draft Contract Vetting |  |  |  | Contract Finalization | [7 empty] | Contract Implementation | [6 empty] | Remarks
[9 empty] | Prep & Submission by Directorate |  | TOR Approval Date |  | Advertise REOI on website |  | Lead-time before Shortlist |  | Submission Date |  | No-objection Date |  | Invitation Date |  | Submission / Opening Date |  | Submission Evaluation Report (T) |  | No Objection evaluation Report (T) |  | Opening Financial Proposals |  | Preparation & Approval (IPC) Eval Report (T)(F) |  | Negotiation (N) |  | Submission Date |  | No-objection Date |  |  | Contract Award |  | Contract Signature |  |  |  |  | Mobilization Advance Payment |  | Draft Report / Commencement |  | Final Report
Description* | Reference Number | Department | Source of Funding | Selection Method | Lumpsum or Time-Based | Estimated Amount | Actual Amount in US $ | Approval Authority | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Contract Amount in US$ '000 | Plan | Actual | Plan | Actual | PR No. | PO No. | BUYER | Plan | Actual | Plan | Actual | Plan | Actual | Final Cost |  | DaysK4
Consultancy Services to conduct Situation Analysis on Environmental Governance | 1/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 20000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy for Technical Advisory Services to Africa Regional Group- to the African Ambassadors in Rome and Rome Based UN agencies | 2/AUDA/DPDC/ENVIR/DC/2020 | DPDC | MSC | ICS | Lumpsum | 50000 | 50000 | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy to conduct desk reviews and assessments on incubation centers in 5 countries | 3/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 15000 |  | Head of Procurement/Director | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services to develop investment plans for Zimbabwe and Malawi | 4/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 40000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services to develop investment plans for Cote d'Ivoire and Comoros | 5/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 40000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services to conduct infrastructure projects feasibility studies | 6/AUDA/DPDC/ENV/QCBS/2020 | DPDC | KFW | QCBS | Lumpsum | 100000 |  | IPC - AUDA-NEPAD | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-09-01 |  | 2020-09-15 |  | 2020-09-29 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-10-11 |  | 2020-10-23 |  | 2020-10-28 |  |  | 2020-10-30 |  | 2020-11-06 |  |  |  |  | n/a | n/a | 2020-11-20
Consultancy services to provide construction supervision for AFRIM | 7/AUDA/DPDC/ENV/QCBS/2020 | DPDC | KFW | QCBS | Time-Based | 170000 |  | IPC - AUC | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-09-01 |  | 2020-09-15 |  | 2020-09-29 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-10-11 |  | 2020-10-23 |  | 2020-10-28 |  |  | 2020-10-30 |  | 2020-11-06 |  |  |  |  | n/a | n/a | 2020-11-20
Consultancy services to Support Capacity and Monitoring System Development and Local Government Planning in Niger | 8/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 15000 |  | Head of Procurement/Director | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services to Support Capacity and Monitoring System Development and Local Government Planning in Uganda | 9/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 15000 |  | Head of Procurement/Director | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services to support AFIRM implementation at country level (2 focal persons) | 10/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 20000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services to conduct training on newly developed land governance mainstreaming tool | 11/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | SSS | Lumpsum | 30000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-14 |  | 2020-07-09 |  | 2020-07-17 |  | 2020-07-22 |  |  | 2020-07-24 |  | 2020-07-31 |  |  |  |  | n/a | n/a | 2020-08-14
Consultancy services to conduct an assessment on country land data rescue for 10 participating Countries in the LGP | 12/AUDA/DPDC/ENV/QCBS/2020 | DPDC | MSC | QCBS | Lumpsum | 50000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-09-01 |  | 2020-09-15 |  | 2020-09-29 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-10-11 |  | 2020-10-23 |  | 2020-10-28 |  |  | 2020-10-30 |  | 2020-11-06 |  |  |  |  | n/a | n/a | 2020-11-20
Consultancy Services to Review Framework for Deploying Technical Network Partners to Augment RAIP/NAIP Implementation Capacity | 13/AUDA/DPDC/ENV/ICS/2020 | DPDC | AGRA | ICS | Lumpsum | 45000 |  | CEO | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Consultancy Services on Continental Assessment on the Application of the Joint Sector Review (JSR) Process to Support Delivery | 14/AUDA/DPDC/ENV/ICS/2020 | DPDC | AGRA | ICS | Lumpsum | 45000 |  | CEO | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Consultancy Services for Final /Mid-Term Review of existing NAIPs in selected countries in Africa ( Zambia) | 15/AUDA/DPDC/ENV/ICS/2020 | DPDC | AGRA | ICS | Lumpsum | 60000 |  | IPC - AUDA-NEPAD | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Consultancy Services for NAIP and RAIP Formulation and Implementation Synthesis of Lessons Learned | 16/AUDA/DPDC/ENV/ICS/2020 | DPDC | AGRA | ICS | Lumpsum | 45000 |  | CEO | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Consultancy Services to formulate a new National Agriculture Investment Plan | 17/AUDA/DPDC/ENV/ICS/2020 | DPDC | AGRA | ICS | Lumpsum | 60000 |  | IPC - AUDA-NEPAD | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Consultancy Services for Independent Technical Review of NAIP of Cameroon | 18/AUDA/DPDC/ENV/ICS/2020 | DPDC | AGRA | ICS | Lumpsum | 45000 |  | CEO | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Consultancy services to conduct regional studies on the feasibility of Bio energy development in the UEMOA region | 19/AUDA/DPDC/ENV/QCBS/2020 | DPDC | UEMOA | QCBS | Lumpsum | 200000 |  | IPC - AUC | 2019-10-15 | 2019-10-07 | 2019-10-20 | 2019-10-07 | 2019-10-23 | 2019-10-07 | 2019-11-06 | 2019-10-22 | 2019-11-20 | 2020-02-07 | 2019-12-04 | 2020-02-22 | 2019-12-07 | 2020-02-22 | 2020-01-06 |  | 2020-01-20 |  | 2020-02-03 |  | 2020-02-10 |  | 2020-02-24 |  | 2020-02-15 |  | 2020-02-27 |  | 2020-03-03 |  |  | 2020-03-05 |  | 2020-03-12 |  |  |  |  | n/a | n/a | 2020-03-26
Consultancy services to produce 6 Project concept memoranda | 20/AUDA/DPDC/EI/ICS/2020 | DPDC | MS | ICS | Lumpsum | 20000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services for Identification process of 6 PIDA projects for technical assistance (SDM) | 21/AUDA/DPDC/EI/ICS/2020 | DPDC | MS | ICS | Lumpsum | 20000 |  | CEO | 2020-06-11 |  | 2020-06-16 |  | 2020-06-19 |  | 2020-07-03 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-17 |  | n/a | n/a | n/a | n/a | 2020-07-27 |  | 2020-07-22 |  | 2020-07-30 |  | 2020-08-04 |  |  | 2020-08-06 |  | 2020-08-13 |  |  |  |  | n/a | n/a | 2020-08-27
Consultancy Services to Develop institutional and governance structure for the CBN | 22/AUDA/DPDC/EI/ICS/2020 | DPDC | MS | ICS | Lumpsum | 20000 |  | CEO | 2020-06-12 |  | 2020-06-17 |  | 2020-06-20 |  | 2020-07-04 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-18 |  | n/a | n/a | n/a | n/a | 2020-07-28 |  | 2020-07-23 |  | 2020-07-31 |  | 2020-08-05 |  |  | 2020-08-07 |  | 2020-08-14 |  |  |  |  | n/a | n/a | 2020-08-28
Consultancy services to Enhance functionality and delivery of the job creation toolkit (SDM) | 23/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 180000 |  | IPC - AUC | 2020-06-13 |  | 2020-06-18 |  | 2020-06-21 |  | 2020-07-05 |  | 2020-07-19 |  | 2020-08-02 |  | 2020-08-05 |  | 2020-09-04 |  | 2020-09-18 |  | 2020-10-02 |  | 2020-10-09 |  | 2020-10-23 |  | 2020-10-14 |  | 2020-10-26 |  | 2020-10-31 |  |  | 2020-11-02 |  | 2020-11-09 |  |  |  |  | n/a | n/a | 2020-11-23
Consultancy services to conduct Feasibility Study for Trans Maghreb Corridor SEZ Study | 24/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 200000 |  | IPC - AUC | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | 2020-07-07 |  | 2020-07-21 |  | 2020-07-24 |  | 2020-08-23 |  | 2020-09-06 |  | 2020-09-20 |  | 2020-09-27 |  | 2020-10-11 |  | 2020-10-02 |  | 2020-10-14 |  | 2020-10-19 |  |  | 2020-10-21 |  | 2020-10-28 |  |  |  |  | n/a | n/a | 2020-11-11
Consultancy services to conduct Feasibility Study for Trans Gambia Corridor SEZ Study | 25/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 200000 |  | IPC - AUC | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-09-01 |  | 2020-09-15 |  | 2020-09-29 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-10-11 |  | 2020-10-23 |  | 2020-10-28 |  |  | 2020-10-30 |  | 2020-11-06 |  |  |  |  | n/a | n/a | 2020-11-20
Consultancy services to conduct Continental Transmission Masterplan Studies | 26/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 860000 |  | IPC - AUC | 2020-06-11 |  | 2020-06-16 |  | 2020-06-19 |  | 2020-07-03 |  | 2020-07-17 |  | 2020-07-31 |  | 2020-08-03 |  | 2020-09-02 |  | 2020-09-16 |  | 2020-09-30 |  | 2020-10-07 |  | 2020-10-21 |  | 2020-10-12 |  | 2020-10-24 |  | 2020-10-29 |  |  | 2020-10-31 |  | 2020-11-07 |  |  |  |  | n/a | n/a | 2020-11-21
Consultancy services to conduct PPP training | 27/AUDA/DPDC/EI/ICS/2020 | DPDC | MS | ICS | Lumpsum | 70000 |  | IPC - AUDA-NEPAD | 2020-06-12 |  | 2020-06-17 |  | 2020-06-20 |  | 2020-07-04 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-18 |  | n/a | n/a | n/a | n/a | 2020-07-28 |  | 2020-07-23 |  | 2020-07-31 |  | 2020-08-05 |  |  | 2020-08-07 |  | 2020-08-14 |  |  |  |  | n/a | n/a | 2020-08-28
Consultancy services for Development of PPP Frameworks | 28/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 70000 |  | IPC - AUDA-NEPAD | 2020-06-13 |  | 2020-06-18 |  | 2020-06-21 |  | 2020-07-05 |  | 2020-07-19 |  | 2020-08-02 |  | 2020-08-05 |  | 2020-09-04 |  | 2020-09-18 |  | 2020-10-02 |  | 2020-10-09 |  | 2020-10-23 |  | 2020-10-14 |  | 2020-10-26 |  | 2020-10-31 |  |  | 2020-11-02 |  | 2020-11-09 |  |  |  |  | n/a | n/a | 2020-11-23
Consultancy services to develop InfraYouth Intitiative Operational Plans | 29/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 50000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-09-01 |  | 2020-09-15 |  | 2020-09-29 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-10-11 |  | 2020-10-23 |  | 2020-10-28 |  |  | 2020-10-30 |  | 2020-11-06 |  |  |  |  | n/a | n/a | 2020-11-20
Consultancy Services to develop SMEs and PPP Identification strategy | 30/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 50000 |  | CEO | 2020-06-11 |  | 2020-06-16 |  | 2020-06-19 |  | 2020-07-03 |  | 2020-07-17 |  | 2020-07-31 |  | 2020-08-03 |  | 2020-09-02 |  | 2020-09-16 |  | 2020-09-30 |  | 2020-10-07 |  | 2020-10-21 |  | 2020-10-12 |  | 2020-10-24 |  | 2020-10-29 |  |  | 2020-10-31 |  | 2020-11-07 |  |  |  |  | n/a | n/a | 2020-11-21
Consultancy Services to conduct Studies for the Roadmap for development of competitive electricity market in UMA and Egypt | 31/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 210000 |  | IPC - AUC | 2020-08-01 |  | 2020-08-06 |  | 2020-08-09 |  | 2020-08-23 |  | 2020-09-06 |  | 2020-09-20 |  | 2020-09-23 |  | 2020-10-23 |  | 2020-11-06 |  | 2020-11-20 |  | 2020-11-27 |  | 2020-12-11 |  | 2020-12-02 |  | 2020-12-14 |  | 2020-12-19 |  |  | 2020-12-21 |  | 2020-12-28 |  |  |  |  | n/a | n/a | 2021-01-11
Consultancy services for Development of Model Laws for e-Commerce and Cybersecurity | 32/AUDA/DPDC/EI/QCBS/2020 | DPDC | MS | QCBS | Lumpsum | 100000 |  | IPC - AUDA-NEPAD | 2020-08-01 |  | 2020-08-06 |  | 2020-08-09 |  | 2020-08-23 |  | 2020-09-06 |  | 2020-09-20 |  | 2020-09-23 |  | 2020-10-23 |  | 2020-11-06 |  | 2020-11-20 |  | 2020-11-27 |  | 2020-12-11 |  | 2020-12-02 |  | 2020-12-14 |  | 2020-12-19 |  |  | 2020-12-21 |  | 2020-12-28 |  |  |  |  | n/a | n/a | 2021-01-11
Consultancy to design and develop the AU Technical Assistance and Exchange Programme for enhanced Partnerships to Support Agenda 2063 Implementation. | 33/AUDA/TCPF/TCP/QCBS/2020 | DTCPF | BMGF | QCBS | Lumpsum | 75000 |  | IPC - AUDA-NEPAD | 2020-06-05 |  | 2020-06-10 |  | 2020-06-13 |  | 2020-06-27 |  | 2020-07-11 |  | 2020-07-25 |  | 2020-07-28 |  | 2020-08-27 |  | 2020-09-10 |  | 2020-09-24 |  | 2020-10-01 |  | 2020-10-15 |  | 2020-10-06 |  | 2020-10-18 |  | 2020-10-23 |  |  | 2020-10-25 |  | 2020-11-01 |  |  |  |  | n/a | n/a | 2020-11-15
Consultancy services for training of senior & management staff on IPSAS | 34/AUDA/DO/FIN/CQS/2020 | DO | MS | CQS | Lumpsum | 45000 |  | CEO | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | 2020-07-07 |  | 2020-07-21 |  | 2020-07-24 |  | 2020-08-07 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-04 |  | 2020-08-21 |  | 2020-09-07 |  | 2020-09-12 |  |  | 2020-09-14 |  | 2020-09-21 |  |  |  |  | n/a | n/a | 2020-10-05
Consultancy services of a Recruitment Firm on approved AUDA-NEPAD Structure | 35/AUDA/DO/HR/QCBS/2020 | DO | MS | QCBS | Lumpsum | 100000 |  | IPC - AUDA-NEPAD | 2020-04-15 |  | 2020-04-20 |  | 2020-04-23 |  | 2020-05-07 |  | 2020-05-21 |  | 2020-06-04 |  | 2020-06-07 |  | 2020-07-07 |  | 2020-07-21 |  | 2020-08-04 |  | 2020-08-11 |  | 2020-08-25 |  | 2020-08-16 |  | 2020-08-28 |  | 2020-09-02 |  |  | 2020-09-04 |  | 2020-09-11 |  |  |  |  | n/a | n/a | 2020-09-25
Recruit consulting firm to conduct leadership training for senior management | 36/AUDA/DO/HR/CQS/2020 | DO | MS | CQS | Lumpsum | 30000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-08-16 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-13 |  | 2020-08-30 |  | 2020-09-16 |  | 2020-09-21 |  |  | 2020-09-23 |  | 2020-09-30 |  |  |  |  | n/a | n/a | 2020-10-14
Consultancy services for training of staff on Leadership | 37/AUDA/DO/HR/IC/2020 | DO | MS | ICS | Lumpsum | 20000 |  | CEO | 2020-06-11 |  | 2020-06-16 |  | 2020-06-19 |  | 2020-07-03 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-17 |  | n/a | n/a | n/a | n/a | 2020-07-27 |  | 2020-07-22 |  | 2020-07-30 |  | 2020-08-04 |  |  | 2020-08-06 |  | 2020-08-13 |  |  |  |  | n/a | n/a | 2020-08-27
Consultancy services for Professional training of HR staff on Management | 38/AUDA/DO/HR/CQS/2020 | DO | MS | CQS | Lumpsum | 20000 |  | CEO | 2020-06-12 |  | 2020-06-17 |  | 2020-06-20 |  | 2020-07-04 |  | 2020-07-18 |  | 2020-08-01 |  | 2020-08-04 |  | 2020-08-18 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-15 |  | 2020-09-01 |  | 2020-09-18 |  | 2020-09-23 |  |  | 2020-09-25 |  | 2020-10-02 |  |  |  |  | n/a | n/a | 2020-10-16
Consultancy services to transfer SAP HANA application platform from SAP data centre to a new data centre in Africa | 39/AUDA/DO/ERP/QCBS/2020 | DO | MS | QCBS | Lumpsum | 250000 |  | IPC - AUC | 2020-06-13 |  | 2020-06-18 |  | 2020-06-21 |  | 2020-07-05 |  | 2020-07-19 |  | 2020-08-02 |  | 2020-08-05 |  | 2020-09-04 |  | 2020-09-18 |  | 2020-10-02 |  | 2020-10-09 |  | 2020-10-23 |  | 2020-10-14 |  | 2020-10-26 |  | 2020-10-31 |  |  | 2020-11-02 |  | 2020-11-09 |  |  |  |  | n/a | n/a | 2020-11-23
Consultancy services to support Promottion of Africa Kaizen initiative in 2020 | 40/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS | Lumpsum | 25000 |  | CEO | 2020-01-23 |  | 2020-01-28 |  | 2020-01-31 |  | 2020-02-14 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-02-28 |  | n/a | n/a | n/a | n/a | 2020-03-09 |  | 2020-03-04 |  | 2020-03-12 |  | 2020-03-17 |  |  | 2020-03-19 |  | 2020-03-26 |  |  |  |  | n/a | n/a | 2020-04-09
Consultancy services for Establishement of digital workplace | 41/AUDA/DO/MIS/QCBS/2020 | DO | MS | QCBS | Lumpsum | 60000 |  | IPC - AUDA-NEPAD | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | 2020-07-16 |  | 2020-07-30 |  | 2020-08-02 |  | 2020-09-01 |  | 2020-09-15 |  | 2020-09-29 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-10-11 |  | 2020-10-23 |  | 2020-10-28 |  |  | 2020-10-30 |  | 2020-11-06 |  |  |  |  | n/a | n/a | 2020-11-20
Consultancy services for Enhancement of Internal Security Network | 42/AUDA/DO/MIS/CQS/2020 | DO | MS | CQS | Lumpsum | 22000 |  | CEO | 2020-08-01 |  | 2020-08-06 |  | 2020-08-09 |  | 2020-08-23 |  | 2020-09-06 |  | 2020-09-20 |  | 2020-09-23 |  | 2020-10-07 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-11-04 |  | 2020-10-21 |  | 2020-11-07 |  | 2020-11-12 |  |  | 2020-11-14 |  | 2020-11-21 |  |  |  |  | n/a | n/a | 2020-12-05
Consultancy services for training of IT staff | 43/AUDA/DO/MIS/ICS/2020 | DO | MS | ICS | Lumpsum | 42000 |  | CEO | 2020-06-23 |  | 2020-06-28 |  | 2020-07-01 |  | 2020-07-15 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-29 |  | n/a | n/a | n/a | n/a | 2020-08-08 |  | 2020-08-03 |  | 2020-08-11 |  | 2020-08-16 |  |  | 2020-08-18 |  | 2020-08-25 |  |  |  |  | n/a | n/a | 2020-09-08
Consultancy services for training of end users on IT | 44/AUDA/DO/MIS/CQS/2020 | DO | MS | CQS | Lumpsum | 48000 |  | CEO | 2020-07-23 |  | 2020-07-28 |  | 2020-07-31 |  | 2020-08-14 |  | 2020-08-28 |  | 2020-09-11 |  | 2020-09-14 |  | 2020-09-28 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-10-26 |  | 2020-10-12 |  | 2020-10-29 |  | 2020-11-03 |  |  | 2020-11-05 |  | 2020-11-12 |  |  |  |  | n/a | n/a | 2020-11-26
Consultancy services for Development of internal applications: (System Automation) | 40/AUDA/DO/MIS/IC/2020 | DO | MS | ICS | Lumpsum | 10000 |  | Head of Procurement/Director | 2020-05-10 |  | 2020-05-15 |  | 2020-05-18 |  | 2020-06-01 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-15 |  | n/a | n/a | n/a | n/a | 2020-06-25 |  | 2020-06-20 |  | 2020-06-28 |  | 2020-07-03 |  |  | 2020-07-05 |  | 2020-07-12 |  |  |  |  | n/a | n/a | 2020-07-26
Project Advisor – stakeholder engagements and partnership building for high speed rail network | 46/AUDA/DPDC/EI/ICS/2020 | DPDC | MS | ICS |  | 60000 | 50000 | IPC - AUDA-NEPAD | 2020-02-01 | 2020-02-12 | 2020-02-06 | 2020-02-12 | 2020-02-09 | 2020-02-12 | 2020-02-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-03-08 |  | n/a | n/a | n/a | n/a | 2020-03-18 |  | 2020-03-13 |  | 2020-03-21 |  | 2020-03-26 |  |  | 2020-03-28 |  | 2020-04-04 | 2020-03-24
Consultant services to develop the programme document for Education and Training Programme | 47/AUDA/DPDC/EDU/ICS/2020 | DPDC | MS | ICS |  | 25000 |  | CEO | 2020-06-27 |  | 2020-07-02 |  | 2020-07-05 |  | 2020-07-19 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-02 |  | n/a | n/a | n/a | n/a | 2020-08-12 |  | 2020-08-07 |  | 2020-08-15 |  | 2020-08-20 |  |  | 2020-08-22 |  | 2020-08-29 |  |  |  |  | n/a | n/a | 2020-09-12
Consultant services to develop implementation plan for Education and Training Programme | 48/AUDA/DPDC/EDU/ICS/2020 | DPDC | MS | ICS |  | 28000 |  | CEO | 2020-06-28 |  | 2020-07-03 |  | 2020-07-06 |  | 2020-07-20 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-03 |  | n/a | n/a | n/a | n/a | 2020-08-13 |  | 2020-08-08 |  | 2020-08-16 |  | 2020-08-21 |  |  | 2020-08-23 |  | 2020-08-30 |  |  |  |  | n/a | n/a | 2020-09-13
Consultant services to develop training modules for the STEM education project | 49/AUDA/DPDC/EDU/ICS/2020 | DPDC | MS | ICS |  | 40000 |  | CEO | 2020-06-29 |  | 2020-07-04 |  | 2020-07-07 |  | 2020-07-21 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-04 |  | n/a | n/a | n/a | n/a | 2020-08-14 |  | 2020-08-09 |  | 2020-08-17 |  | 2020-08-22 |  |  | 2020-08-24 |  | 2020-08-31 |  |  |  |  | n/a | n/a | 2020-09-14
Consultant services to compile mid-year country report for STEM Education Project | 50/AUDA/DPDC/EDU/ICS/2020 | DPDC | MS | ICS |  | 46000 |  | CEO | 2020-07-01 |  | 2020-07-06 |  | 2020-07-09 |  | 2020-07-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-06 |  | n/a | n/a | n/a | n/a | 2020-08-16 |  | 2020-08-11 |  | 2020-08-19 |  | 2020-08-24 |  |  | 2020-08-26 |  | 2020-09-02 |  |  |  |  | n/a | n/a | 2020-09-16
Consultant services to edit articles from country teams as a book for publication | 51/AUDA/DPDC/EDU/ICS/2020 | DPDC | MS | ICS |  | 60000 |  | IPC - AUDA-NEPAD | 2020-10-01 |  | 2020-10-06 |  | 2020-10-09 |  | 2020-10-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-11-06 |  | n/a | n/a | n/a | n/a | 2020-11-16 |  | 2020-11-11 |  | 2020-11-19 |  | 2020-11-24 |  |  | 2020-11-26 |  | 2020-12-03 |  |  |  |  | n/a | n/a | 2020-12-17
Individual consultant Industrial Policy Research and Development of AUDA-NEPAD Industrialisation Programme Content (Baseline reviews and appraisal of National and Regional Industrialization plans/strategies; National Development Plans and Other Sector Plans) | 52/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 60000 |  | IPC - AUDA-NEPAD | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-07 |  | n/a | n/a | n/a | n/a | 2020-07-17 |  | 2020-07-12 |  | 2020-07-20 |  | 2020-07-25 |  |  | 2020-07-27 |  | 2020-08-03 |  |  |  |  | n/a | n/a | 2020-08-17
Undertake appraisal-analysis to cluster AU member states into distinguished economic complementarity clusters as basis to foster regional/multi-national Industrial value chains | 53/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 50000 |  | CEO | 2020-06-02 |  | 2020-06-07 |  | 2020-06-10 |  | 2020-06-24 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-08 |  | n/a | n/a | n/a | n/a | 2020-07-18 |  | 2020-07-13 |  | 2020-07-21 |  | 2020-07-26 |  |  | 2020-07-28 |  | 2020-08-04 |  |  |  |  | n/a | n/a | 2020-08-18
Individual Consultant to Develop a website for the World Aquaculture Society African Chapter | 54/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-03 |  | 2020-06-08 |  | 2020-06-11 |  | 2020-06-25 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-09 |  | n/a | n/a | n/a | n/a | 2020-07-19 |  | 2020-07-14 |  | 2020-07-22 |  | 2020-07-27 |  |  | 2020-07-29 |  | 2020-08-05 |  |  |  |  | n/a | n/a | 2020-08-19
Indivudula Consultant to Undertake a foresight and mapping study on Blue Economy for the continent | 55/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 30000 |  | CEO | 2020-06-04 |  | 2020-06-09 |  | 2020-06-12 |  | 2020-06-26 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-10 |  | n/a | n/a | n/a | n/a | 2020-07-20 |  | 2020-07-15 |  | 2020-07-23 |  | 2020-07-28 |  |  | 2020-07-30 |  | 2020-08-06 |  |  |  |  | n/a | n/a | 2020-08-20
Individual Consultant to Produce a briefing document for the African Regional Group of Ambassadors for the FAO Committee on Fisheries (COFI) including analysis of the FAO agenda doc. to produce the briefing doc for Africa; translation into relevant languages; production and printing | 56/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 20000 |  | CEO | 2020-06-05 |  | 2020-06-10 |  | 2020-06-13 |  | 2020-06-27 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-11 |  | n/a | n/a | n/a | n/a | 2020-07-21 |  | 2020-07-16 |  | 2020-07-24 |  | 2020-07-29 |  |  | 2020-07-31 |  | 2020-08-07 |  |  |  |  | n/a | n/a | 2020-08-21
Consultant to prepare Country assessement Reports | 57/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 60000 |  | CEO | 2020-06-06 |  | 2020-06-11 |  | 2020-06-14 |  | 2020-06-28 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-12 |  | n/a | n/a | n/a | n/a | 2020-07-22 |  | 2020-07-17 |  | 2020-07-25 |  | 2020-07-30 |  |  | 2020-08-01 |  | 2020-08-08 |  |  |  |  | n/a | n/a | 2020-08-22
Advocacy for BPO services for Youth Opportunity | 58/AUDA/DPDC/IND/IC/2020 | DPDC | MS | ICS |  | 45000 |  | CEO | 2020-06-07 |  | 2020-06-12 |  | 2020-06-15 |  | 2020-06-29 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-13 |  | n/a | n/a | n/a | n/a | 2020-07-23 |  | 2020-07-18 |  | 2020-07-26 |  | 2020-07-31 |  |  | 2020-08-02 |  | 2020-08-09 |  |  |  |  | n/a | n/a | 2020-08-23
Hire a Lead facilitator and team of moderators (as a firm and individuals as Moderators) | 59/AUDA/DPDC/SKI/LCS/2020 | DPDC | MS | LCS |  | 30000 |  | CEO | 2020-06-08 |  | 2020-06-13 |  | 2020-06-16 |  | 2020-06-30 |  | 2020-07-14 |  | 2020-07-28 |  | 2020-07-31 |  | 2020-08-30 |  | 2020-09-13 |  | 2020-09-27 |  | 2020-10-04 |  | 2020-10-18 |  | 2020-10-09 |  | 2020-10-21 |  | 2020-10-26 |  |  | 2020-10-28 |  | 2020-11-04 |  |  |  |  | n/a | n/a | 2020-11-18
Hire Expert Consultants to support thematic development and meeting facilitation x 3(100 000 SMEs, SVAI and ACJ! conference) | 60/AUDA/DPDC/SKI/LCS/2020 | DPDC | MS | LCS |  | 35000 |  | CEO | 2020-06-09 |  | 2020-06-14 |  | 2020-06-17 |  | 2020-07-01 |  | 2020-07-15 |  | 2020-07-29 |  | 2020-08-01 |  | 2020-08-31 |  | 2020-09-14 |  | 2020-09-28 |  | 2020-10-05 |  | 2020-10-19 |  | 2020-10-10 |  | 2020-10-22 |  | 2020-10-27 |  |  | 2020-10-29 |  | 2020-11-05 |  |  |  |  | n/a | n/a | 2020-11-19
Hiring consultant to carry out the development of the Master Trainer concept and curriculum | 61/AUDA/DPDC/SKI/ICS/2020 | DPDC | MS | ICS |  | 30000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Hiring consultant to domesticate WEAI for AUDA role out | 62/AUDA/DPDC/SKI/ICS/2020 | DPDC | MS | ICS |  | 30000 |  | CEO | 2020-06-11 |  | 2020-06-16 |  | 2020-06-19 |  | 2020-07-03 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-17 |  | n/a | n/a | n/a | n/a | 2020-07-27 |  | 2020-07-22 |  | 2020-07-30 |  | 2020-08-04 |  |  | 2020-08-06 |  | 2020-08-13 |  |  |  |  | n/a | n/a | 2020-08-27
Hire a consultant to develop the proposal and partnership framework and curriculum for 100,000 SME's | 63/AUDA/DPDC/SKI/ICS/2020 | DPDC | WB | ICS |  | 20000 |  | CEO | 2020-06-12 |  | 2020-06-17 |  | 2020-06-20 |  | 2020-07-04 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-18 |  | n/a | n/a | n/a | n/a | 2020-07-28 |  | 2020-07-23 |  | 2020-07-31 |  | 2020-08-05 |  |  | 2020-08-07 |  | 2020-08-14 |  |  |  |  | n/a | n/a | 2020-08-28
Provide Member States with technical advisory services on data acquisition tools, instruments and analysis for socio-economic indicators | 64/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 30000 |  | IPC - AUDA-NEPAD | 2020-06-13 |  | 2020-06-18 |  | 2020-06-21 |  | 2020-07-05 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-19 |  | n/a | n/a | n/a | n/a | 2020-07-29 |  | 2020-07-24 |  | 2020-08-01 |  | 2020-08-06 |  |  | 2020-08-08 |  | 2020-08-15 |  |  |  |  | n/a | n/a | 2020-08-29
Strengthening National Planning Platform and Coordination Unit to Support Planning | 65/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 30000 |  | IPC - AUDA-NEPAD | 2020-06-14 |  | 2020-06-19 |  | 2020-06-22 |  | 2020-07-06 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-20 |  | n/a | n/a | n/a | n/a | 2020-07-30 |  | 2020-07-25 |  | 2020-08-02 |  | 2020-08-07 |  |  | 2020-08-09 |  | 2020-08-16 |  |  |  |  | n/a | n/a | 2020-08-30
Technical Cooperation for the implementation of the AUDA Strategic Plan and Review of AUDA-NEPAD engagement with the UN System | 66/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 30000 |  | Head of Procurement/Director | 2020-06-15 |  | 2020-06-20 |  | 2020-06-23 |  | 2020-07-07 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-21 |  | n/a | n/a | n/a | n/a | 2020-07-31 |  | 2020-07-26 |  | 2020-08-03 |  | 2020-08-08 |  |  | 2020-08-10 |  | 2020-08-17 |  |  |  |  | n/a | n/a | 2020-08-31
Development of African Common Positions and support to African Group of Negotiators on Biodiversity | 67/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 30000 |  | Head of Procurement/Director | 2020-06-16 |  | 2020-06-21 |  | 2020-06-24 |  | 2020-07-08 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-22 |  | n/a | n/a | n/a | n/a | 2020-08-01 |  | 2020-07-27 |  | 2020-08-04 |  | 2020-08-09 |  |  | 2020-08-11 |  | 2020-08-18 |  |  |  |  | n/a | n/a | 2020-09-01
Formulation of Intergovernmental Authority on Development (IGAD) Regional Strategy and Implementation Plan 2021-2025 & Delivery of the AUDA-NEPAD Compacts | 68/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 80000 |  | CEO | 2020-06-17 |  | 2020-06-22 |  | 2020-06-25 |  | 2020-07-09 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-23 |  | n/a | n/a | n/a | n/a | 2020-08-02 |  | 2020-07-28 |  | 2020-08-05 |  | 2020-08-10 |  |  | 2020-08-12 |  | 2020-08-19 |  |  |  |  | n/a | n/a | 2020-09-02
[9 empty] | 2020-06-18 |  | 2020-06-23 |  | 2020-06-26 |  | 2020-07-10 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-24 |  | n/a | n/a | n/a | n/a | 2020-08-03 |  | 2020-07-29 |  | 2020-08-06 |  | 2020-08-11 |  |  | 2020-08-13 |  | 2020-08-20 |  |  |  |  | n/a | n/a | 2020-09-03
Develop branding and advocacy support for Tourism in Africa | 70/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 15000 |  | CEO | 2020-06-19 |  | 2020-06-24 |  | 2020-06-27 |  | 2020-07-11 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-25 |  | n/a | n/a | n/a | n/a | 2020-08-04 |  | 2020-07-30 |  | 2020-08-07 |  | 2020-08-12 |  |  | 2020-08-14 |  | 2020-08-21 |  |  |  |  | n/a | n/a | 2020-09-04
Consultancy to Develop guidelines and strategies for safety and security in Tourism | 71/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 40000 |  | Head of Procurement/Director | 2020-06-20 |  | 2020-06-25 |  | 2020-06-28 |  | 2020-07-12 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-26 |  | n/a | n/a | n/a | n/a | 2020-08-05 |  | 2020-07-31 |  | 2020-08-08 |  | 2020-08-13 |  |  | 2020-08-15 |  | 2020-08-22 |  |  |  |  | n/a | n/a | 2020-09-05
Consultancy for the Development of project Document on Rural Tourism | 72/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 25000 |  | CEO | 2020-06-21 |  | 2020-06-26 |  | 2020-06-29 |  | 2020-07-13 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-27 |  | n/a | n/a | n/a | n/a | 2020-08-06 |  | 2020-08-01 |  | 2020-08-09 |  | 2020-08-14 |  |  | 2020-08-16 |  | 2020-08-23 |  |  |  |  | n/a | n/a | 2020-09-06
Leads engagement of stakeholders and partners in its development (leading a multi-directorate team ) | 73/AUDA/PIPD/DIR/ICS/2020 | PIPD | MS | ICS |  | 60000 |  | IPC - AUDA-NEPAD | 2020-06-22 |  | 2020-06-27 |  | 2020-06-30 |  | 2020-07-14 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-28 |  | n/a | n/a | n/a | n/a | 2020-08-07 |  | 2020-08-02 |  | 2020-08-10 |  | 2020-08-15 |  |  | 2020-08-17 |  | 2020-08-24 |  |  |  |  | n/a | n/a | 2020-09-07
Leads engagement of stakeholders and partners in its development (leading a multi-directorate team ) | 74/AUDA/PIPD/DIR/ICS/2020 | PIPD | MS | ICS |  | 60000 |  | IPC - AUDA-NEPAD | 2020-06-23 |  | 2020-06-28 |  | 2020-07-01 |  | 2020-07-15 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-29 |  | n/a | n/a | n/a | n/a | 2020-08-08 |  | 2020-08-03 |  | 2020-08-11 |  | 2020-08-16 |  |  | 2020-08-18 |  | 2020-08-25 |  |  |  |  | n/a | n/a | 2020-09-08
Leads engagement of stakeholders and partners in its development (leading a multi-directorate team ) | 75/AUDA/PIPD/DIR/ICS/2020 | PIPD | MS | ICS |  | 45000 |  | CEO | 2020-06-24 |  | 2020-06-29 |  | 2020-07-02 |  | 2020-07-16 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-30 |  | n/a | n/a | n/a | n/a | 2020-08-09 |  | 2020-08-04 |  | 2020-08-12 |  | 2020-08-17 |  |  | 2020-08-19 |  | 2020-08-26 |  |  |  |  | n/a | n/a | 2020-09-09
Firms to train Staff on Resource Mobilization (multiple sessions throughout the year) | 76/AUDA/DTCPF/RMD/CQS/2020 | DTCPF | MS | CQS |  | 17900 |  | CEO | 2020-06-25 |  | 2020-06-30 |  | 2020-07-03 |  | 2020-07-17 |  | 2020-07-31 |  | 2020-08-14 |  | 2020-08-17 |  | 2020-08-31 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-28 |  | 2020-09-14 |  | 2020-10-01 |  | 2020-10-06 |  |  | 2020-10-08 |  | 2020-10-15 |  |  |  |  | n/a | n/a | 2020-10-29
Individual consultant to train Staff on Resource Mobilization (multiple sessions throughout the year) | 77/AUDA/DTCPF/RMD/ICS/2020 | DTCPF | MS | ICS |  | 17900 |  | CEO | 2020-06-26 |  | 2020-07-01 |  | 2020-07-04 |  | 2020-07-18 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-01 |  | n/a | n/a | n/a | n/a | 2020-08-11 |  | 2020-08-06 |  | 2020-08-14 |  | 2020-08-19 |  |  | 2020-08-21 |  | 2020-08-28 |  |  |  |  | n/a | n/a | 2020-09-11
Audit report for DP funded projects (throughout the year) | 78/AUDA/DTCPF/RMD/LCS/2020 | DTCPF | MS | LCS |  | 40000 |  | CEO | 2020-06-27 |  | 2020-07-02 |  | 2020-07-05 |  | 2020-07-19 |  | 2020-08-02 |  | 2020-08-16 |  | 2020-08-19 |  | 2020-09-18 |  | 2020-10-02 |  | 2020-10-16 |  | 2020-10-23 |  | 2020-11-06 |  | 2020-10-28 |  | 2020-11-09 |  | 2020-11-14 |  |  | 2020-11-16 |  | 2020-11-23 |  |  |  |  | n/a | n/a | 2020-12-07
Individual Consultant for mapping of development partners and crafting of framework and tracking & reporting tool | 79/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS | ICS |  | 45000 |  | CEO | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Individual Consultancy for to develop AUDA-NEPAD digital partnership platform | 80/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-07 |  | n/a | n/a | n/a | n/a | 2020-07-17 |  | 2020-07-12 |  | 2020-07-20 |  | 2020-07-25 |  |  | 2020-07-27 |  | 2020-08-03 |  |  |  |  | n/a | n/a | 2020-08-17
Individual Consultant services for a Pavilion Director for World Expo 2020 -2021 in Dubia | 81/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS | ICS |  | 10000 |  | Head of Procurement/Director | 2020-10-01 |  | 2020-10-06 |  | 2020-10-09 |  | 2020-10-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-11-06 |  | n/a | n/a | n/a | n/a | 2020-11-16 |  | 2020-11-11 |  | 2020-11-19 |  | 2020-11-24 |  |  | 2020-11-26 |  | 2020-12-03 |  |  |  |  | n/a | n/a | 2020-12-17
Consultancy services to conduct an Annual audit of APET-CJED | 82/AUDA/DTCPF/SID/LCS/2020 | DTCPF | MS | LCS |  | 15000 |  | Head of Procurement/Director | 2020-10-01 |  | 2020-10-06 |  | 2020-10-09 |  | 2020-10-23 |  | 2020-11-06 |  | 2020-11-20 |  | 2020-11-23 |  | 2020-12-23 |  | 2021-01-06 |  | 2021-01-20 |  | 2021-01-27 |  | 2021-02-10 |  | 2021-02-01 |  | 2021-02-13 |  | 2021-02-18 |  |  | 2021-02-20 |  | 2021-02-27 |  |  |  |  | n/a | n/a | 2021-03-13
Consultancy services for development of an evaluation database containing reports, status of implementations, recommendations, lessons and inventory of evaluation experts | 83/AUDA/KMPE/ED/ICS/2020 | DKMPE | MS | ICS |  | 20000 |  | CEO | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-07 |  | n/a | n/a | n/a | n/a | 2020-07-17 |  | 2020-07-12 |  | 2020-07-20 |  | 2020-07-25 |  |  | 2020-07-27 |  | 2020-08-03 |  |  |  |  | n/a | n/a | 2020-08-17
Consultancy services for training on search engine optimisation | 84/AUDA/KMPE/KMD/ICS/2020 | DKMPE | MS | ICS |  | 20000 |  | CEO | 2020-06-02 |  | 2020-06-07 |  | 2020-06-10 |  | 2020-06-24 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-08 |  | n/a | n/a | n/a | n/a | 2020-07-18 |  | 2020-07-13 |  | 2020-07-21 |  | 2020-07-26 |  |  | 2020-07-28 |  | 2020-08-04 |  |  |  |  | n/a | n/a | 2020-08-18
Consultancy services for maintenance and Web development of the AUDA-NEPAD Portals and sub-portals | 85/AUDA/KMPE/KMD/QCBS/2020 | DKMPE | MS | QCBS |  | 120000 |  | IPC - AUC | 2020-06-03 |  | 2020-06-08 |  | 2020-06-11 |  | 2020-06-25 |  | 2020-07-09 |  | 2020-07-23 |  | 2020-07-26 |  | 2020-08-25 |  | 2020-09-08 |  | 2020-09-22 |  | 2020-09-29 |  | 2020-10-13 |  | 2020-10-04 |  | 2020-10-16 |  | 2020-10-21 |  |  | 2020-10-23 |  | 2020-10-30 |  |  |  |  | n/a | n/a | 2020-11-13
Consutlancy services for the operationalization of communities of practice | 86/AUDA/KMPE/KMD/QCBS/2020 | DKMPE | MS | QCBS |  | 80000 |  | IPC - AUDA-NEPAD | 2020-06-04 |  | 2020-06-09 |  | 2020-06-12 |  | 2020-06-26 |  | 2020-07-10 |  | 2020-07-24 |  | 2020-07-27 |  | 2020-08-26 |  | 2020-09-09 |  | 2020-09-23 |  | 2020-09-30 |  | 2020-10-14 |  | 2020-10-05 |  | 2020-10-17 |  | 2020-10-22 |  |  | 2020-10-24 |  | 2020-10-31 |  |  |  |  | n/a | n/a | 2020-11-14
Consultancy services for development of knowledge products contents | 87/AUDA/KMPE/KMD/ICS/2020 | DKMPE | MS | ICS |  | 20000 |  | CEO | 2020-06-05 |  | 2020-06-10 |  | 2020-06-13 |  | 2020-06-27 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-11 |  | n/a | n/a | n/a | n/a | 2020-07-21 |  | 2020-07-16 |  | 2020-07-24 |  | 2020-07-29 |  |  | 2020-07-31 |  | 2020-08-07 |  |  |  |  | n/a | n/a | 2020-08-21
Consultancy for the development of AUDA-NEPAD Renewable Energy Deployment Model | 88/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS |  | 36000 |  | CEO | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-07 |  | n/a | n/a | n/a | n/a | 2020-07-17 |  | 2020-07-12 |  | 2020-07-20 |  | 2020-07-25 |  |  | 2020-07-27 |  | 2020-08-03 |  |  |  |  | n/a | n/a | 2020-08-17
Consultancy services to develop Guidelines on Mainstreaming Environmental Governance in Agriculture Transformation | 89/AUDA/DPDC/ENV/ICS/2020 | DPDC | MSC | ICS | Lumpsum | 30000 |  | CEO | 2020-06-10 |  | 2020-06-15 |  | 2020-06-18 |  | 2020-07-02 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-16 |  | n/a | n/a | n/a | n/a | 2020-07-26 |  | 2020-07-21 |  | 2020-07-29 |  | 2020-08-03 |  |  | 2020-08-05 |  | 2020-08-12 |  |  |  |  | n/a | n/a | 2020-08-26
Consultancy services for Senior Continental Power Systems Development Coordinator | 90/AUDA/DPDC/EI/SSS/2020 | DPDC | MSC | SSS |  | 40000 |  | CEO | 2020-03-15 | 2020-02-07 | 2020-03-20 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-03-23 |  | 2020-04-06 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-18 |  | 2020-04-13 |  | 2020-04-21 |  | 2020-04-26 |  |  | 2020-04-28 |  | 2020-05-05 |  |  |  |  | n/a | n/a | 2020-05-19
Consultancy Services for Development of a Policy for AUDA Young Professionals Programme | 91/AUDA/DO/DIR/ICS/2020 | DO | MSC | ICS |  | 18000 |  | CEO | 2020-03-15 |  | 2020-03-20 |  | 2020-03-23 |  | 2020-04-06 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-20 |  | n/a | n/a | n/a | n/a | 2020-04-30 |  | 2020-04-25 |  | 2020-05-03 |  | 2020-05-08 |  |  | 2020-05-10 |  | 2020-05-17 |  |  |  |  | n/a | n/a | 2020-05-31
Consultancy services for Pillar Assessment Audit Preparation and Readiness | 92/AUDA/DO/DIR/SSS/2020 | DO | MSC | SSS |  | 51000 |  | IPC - AUDA-NEPAD | 2020-04-15 |  | 2020-04-20 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-23 |  | 2020-05-07 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-05-19 |  | 2020-05-14 |  | 2020-05-22 |  | 2020-05-27 |  |  | 2020-05-29 |  | 2020-06-05 |  |  |  |  | n/a | n/a | 2020-06-19
Consultancy services for SAP Security and Data Enhancement for Pillar Assessment | 93/AUDA/DO/ERP/ICS/2020 | DO | MSC | ICS |  | 15000 |  | Head of Procurement/Director | 2020-04-15 |  | 2020-04-20 |  | 2020-04-23 |  | 2020-05-07 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-05-21 |  | n/a | n/a | n/a | n/a | 2020-05-31 |  | 2020-05-26 |  | 2020-06-03 |  | 2020-06-08 |  |  | 2020-06-10 |  | 2020-06-17 |  |  |  |  | n/a | n/a | 2020-07-01
Consultancy Services for a Public Health Specialist to support Member States in accelerating containment measures against COVID-19 (COVID related) | 94/AUDA/DPDC/HEA/ICS/2020 | DPDC | MSC | ICS |  | 38000 |  | CEO | 2020-04-30 |  | 2020-05-05 |  | 2020-05-08 |  | 2020-05-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-05 |  | n/a | n/a | n/a | n/a | 2020-06-15 |  | 2020-06-10 |  | 2020-06-18 |  | 2020-06-23 |  |  | 2020-06-25 |  | 2020-07-02 |  |  |  |  | n/a | n/a | 2020-07-16
Consultancy service to conduct Food & Nutrition insecurity vulnerability analysis and modelling under COVID-19 (COVID related) | 95/AUDA/DPDC/ENV/QCBS/2020 | DPDC | MSC | QCBS |  | 55000 |  | CEO | 2020-05-15 |  | 2020-05-20 |  | 2020-05-23 |  | 2020-06-06 |  | 2020-06-20 |  | 2020-07-04 |  | 2020-07-07 |  | 2020-08-06 |  | 2020-08-20 |  | 2020-09-03 |  | 2020-09-10 |  | 2020-09-24 |  | 2020-09-15 |  | 2020-09-27 |  | 2020-10-02 |  |  | 2020-10-04 |  | 2020-10-11 |  |  |  |  | n/a | n/a | 2020-10-25
Editorial International Consultant | 96/AUDA/DPDC/HUM/ICS/2020 | DPDC | MSC | ICS |  | 31200 |  | CEO | 2020-05-20 | 2020-05-26 | 2020-05-25 | 2020-05-26 | 2020-05-28 |  | 2020-06-11 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-25 |  | n/a | n/a | n/a | n/a | 2020-07-05 |  | 2020-06-30 |  | 2020-07-08 |  | 2020-07-13 |  |  | 2020-07-15 |  | 2020-07-22 |  |  |  |  | n/a | n/a | 2020-08-05
Consultancy service to develop a programme document and Curriculum for strategic initiatives | 97/AUDA/DTCPF/DSI/ICS/2020 | DTCPF | MSC | ICS |  | 25000 |  | CEO | 2020-06-02 |  | 2020-06-07 |  | 2020-06-10 |  | 2020-06-24 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-08 |  | n/a | n/a | n/a | n/a | 2020-07-18 |  | 2020-07-13 |  | 2020-07-21 |  | 2020-07-26 |  |  | 2020-07-28 |  | 2020-08-04 |  |  |  |  | n/a | n/a | 2020-08-18
Consultancy for the drafting and Editing of APET reports on AI, Blockchain and Next generation batteries | 98/AUDA/DTCPF/DSI/ICS/2020 | DTCPF | MSC | ICS |  | 35000 |  | CEO | 2020-06-08 |  | 2020-06-13 |  | 2020-06-16 |  | 2020-06-30 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-14 |  | n/a | n/a | n/a | n/a | 2020-07-24 |  | 2020-07-19 |  | 2020-07-27 |  | 2020-08-01 |  |  | 2020-08-03 |  | 2020-08-10 |  |  |  |  | n/a | n/a | 2020-08-24
Consultancy for the development of strategic Document and implementation plan for AUDA NEPAD think thank initiative | 99/AUDA/DTCPF/DSI/ICS/2020 | DTCPF | MSC | ICS |  | 30000 |  | CEO | 2020-06-01 |  | 2020-06-06 |  | 2020-06-09 |  | 2020-06-23 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-07 |  | n/a | n/a | n/a | n/a | 2020-07-17 |  | 2020-07-12 |  | 2020-07-20 |  | 2020-07-25 |  |  | 2020-07-27 |  | 2020-08-03 |  |  |  |  | n/a | n/a | 2020-08-17
Consultancy Services to support consolidation of submissions from SADC Member States and writing of Programme Funding on Tuberculosis in the Mining Sector Phase III | 100/AUDA/DTCPF/DSI/SSS/2020 | DTCPF | MSC | SSS |  | 10000 |  | Head of Procurement/Director | 2020-06-05 |  | 2020-06-10 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-13 |  | 2020-06-27 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-07-09 |  | 2020-07-04 |  | 2020-07-12 |  | 2020-07-17 |  |  | 2020-07-19 |  | 2020-07-26 |  |  |  |  | n/a | n/a | 2020-08-09
Consultancy services to assist in drafting CEOs end of tenure reports for Organisational Development and coherence | 101/AUDA/OCEO/CEO/SSS/2020 | OCEO | MS | SSS |  | 50000 |  | CEO | 2020-05-15 |  | 2020-05-20 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-05-23 |  | 2020-06-06 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-06-18 |  | 2020-06-13 |  | 2020-06-21 |  | 2020-06-26 |  |  | 2020-06-28 |  | 2020-07-05 |  |  |  |  | n/a | n/a | 2020-07-19
Consultant to develop a white-paper on APET response to COVID-19 | 102/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS/DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy to Undertake a joint research and development of knowledge products with MWAPATA Institute | 103/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS/DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Independent Consultant to carry out an annual evaluation of APET/CJED Initiative | 104/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS/DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy service to do training on innovation and emerging technologies knowledge and skills for DSI Staff | 105/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS/DP | ICS |  | 20000 |  | CEO | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy for Planning, facilitation and report writing for APET and CJED virtual meetings and webinars | 106/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS/DP | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy to develop CJED training modules and to conduct trainings for Member States and RECs. | 107/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | MS/DP | ICS |  | 30000 |  | CEO | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultant to assess the performance of STI investment in Africa from 1980 to 2020 | 108/AUDA/DTCPF/TCP/ICS/2020 | DTCPF | BMGF | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Develop Program Operation Manual of the Strategic Plan and SOPs for the PIPD | 109/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 27500 |  | CEO | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy Services for the Reviewing of Megatrends and Various Documents to Support the Drafting of Strategic Plan for (AUDA-NEPAD) 202-2023 PIPD Directorate | 110/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | ICS |  | 12500 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy services to Develop AUDA Development Fund and its establishment and full operationalisation | 111/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | QCBS |  | 90000 |  | IPC - AUDA-NEPAD | 2020-07-15 |  | 2020-07-20 |  | 2020-07-23 |  | 2020-08-06 |  | 2020-08-20 |  | 2020-09-03 |  | 2020-09-06 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-11-03 |  | 2020-11-10 |  | 2020-11-24 |  | 2020-11-15 |  | 2020-11-27 |  | 2020-12-02 |  |  | 2020-12-04 |  | 2020-12-11 |  |  |  |  | n/a | n/a | 2020-12-25
Consultancy services to prepare Post-COVID report to support Member states recovery on Tourism | 112/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 18000 |  | CEO | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
consultant for the production of 3rd Edition of the Rural Futures Atlas | 113/AUDA/PIPD/TCAS/ICS/2020 | PIPD | MS | QCBS |  | 60000 |  | IPC - AUDA-NEPAD | 2020-07-15 |  | 2020-07-20 |  | 2020-07-23 |  | 2020-08-06 |  | 2020-08-20 |  | 2020-09-03 |  | 2020-09-06 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-11-03 |  | 2020-11-10 |  | 2020-11-24 |  | 2020-11-15 |  | 2020-11-27 |  | 2020-12-02 |  |  | 2020-12-04 |  | 2020-12-11 |  |  |  |  | n/a | n/a | 2020-12-25
Hire consultant for Production of Knowledge Product for the ASTF/FAO project | 114/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 20000 |  | CEO | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
individual consultant to identify Youth Best practices | 115/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultant to create National Action Plan (NAP) for rural youth in employment in Mali | 116/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultant to create National Action Plan (NAP) for rural youth in employment in Mozambique | 117/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultant to create National Action Plan (NAP) for rural youth in employment in Zambia. | 118/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 10000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultants to produce Training Model and strengthening of Curricula, plus identify gaps on existing IFAD projects in Cameroon | 119/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultants to produce Training Model and strengthening of Curricula, plus identify gaps on existing IFAD projects in Mali | 120/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultants to produce Training Model and strengthening of Curricula, plus identify gaps on existing IFAD projects in Mozambique | 121/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultants to produce Training Model and strengthening of Curricula, plus identify gaps on existing IFAD projects in Zambia | 122/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Junior consultant to conduct ASTF/FAO end of project evaluation and prepare report | 123/AUDA/PIPD/TCAS/ICS/2020 | PIPD | DP | ICS |  | 15000 |  | Head of Procurement/Director | 2020-06-30 |  | 2020-07-05 |  | 2020-07-08 |  | 2020-07-22 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-05 |  | n/a | n/a | n/a | n/a | 2020-08-15 |  | 2020-08-10 |  | 2020-08-18 |  | 2020-08-23 |  |  | 2020-08-25 |  | 2020-09-01 |  |  |  |  | n/a | n/a | 2020-09-15
Consultancy to create market insights and business intelligence through comprehensive market analysis by country/value chain in 5 Countries | 124/AUDA/OCEO/GROW/QCBS/2020 | OCEO | AfDB/MS | QCBS | Lumpsum | 120000 |  | IPC - AUC | 2020-07-15 |  | 2020-07-20 |  | 2020-07-23 |  | 2020-08-06 |  | 2020-08-20 |  | 2020-09-03 |  | 2020-09-06 |  | 2020-10-06 |  | 2020-10-20 |  | 2020-11-03 |  | 2020-11-10 |  | 2020-11-24 |  | 2020-11-15 |  | 2020-11-27 |  | 2020-12-02 |  |  | 2020-12-04 |  | 2020-12-11 |  |  |  |  | n/a | n/a | 2020-12-25
Consultancy for provision of Client Services for the Agribusiness Engine – i.e. Creation of factsheets/profiles/outlines of specific business opportunities for investment | 125/AUDA/OCEO/GROW/ICS/2020 | OCEO | AfDB/MS | ICS |  | 28000 |  | CEO | 2020-07-16 |  | 2020-07-21 |  | 2020-07-24 |  | 2020-08-07 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2020-08-21 |  | n/a | n/a | n/a | n/a | 2020-08-31 |  | 2020-08-26 |  | 2020-09-03 |  | 2020-09-08 |  |  | 2020-09-10 |  | 2020-09-17 |  |  |  |  | n/a | n/a | 2020-10-01
Consultancy for development of 50 bankable business cases for companies investing in prioritised agriculture value chains. | 126/AUDA/OCEO/GROW/QCBS/2020 | OCEO | AfDB/MS | QCBS | Lumpsum | 350000 |  | IPC - AUC | 2020-10-30 |  | 2020-11-04 |  | 2020-11-07 |  | 2020-11-21 |  | 2020-12-05 |  | 2020-12-19 |  | 2020-12-22 |  | 2021-01-21 |  | 2021-02-04 |  | 2021-02-18 |  | 2021-02-25 |  | 2021-03-11 |  | 2021-03-02 |  | 2021-03-14 |  | 2021-03-19 |  |  | 2021-03-21 |  | 2021-03-28 |  |  |  |  | n/a | n/a | 2021-04-11
Consultancy for Client matchmaking for Building targeted value chain farm to fork alliances | 127/AUDA/OCEO/GROW/CQS/2020 | OCEO | AfDB/MS | CQS |  | 75000 |  | IPC - AUDA-NEPAD | 2020-06-25 |  | 2020-06-30 |  | 2020-07-03 |  | 2020-07-17 |  | 2020-07-31 |  | 2020-08-14 |  | 2020-08-17 |  | 2020-08-31 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-28 |  | 2020-09-14 |  | 2020-10-01 |  | 2020-10-06 |  |  | 2020-10-08 |  | 2020-10-15 |  |  |  |  | n/a | n/a | 2020-10-29
Consultancy for establishment of a continental “client relationship” networkand Management | 128/AUDA/OCEO/GROW/CQS/2020 | OCEO | AfDB/MS | CQS |  | 60000 |  | IPC - AUDA-NEPAD | 2020-06-25 |  | 2020-06-30 |  | 2020-07-03 |  | 2020-07-17 |  | 2020-07-31 |  | 2020-08-14 |  | 2020-08-17 |  | 2020-08-31 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-28 |  | 2020-09-14 |  | 2020-10-01 |  | 2020-10-06 |  |  | 2020-10-08 |  | 2020-10-15 |  |  |  |  | n/a | n/a | 2020-10-29
Consultancy for design and establishment of a Customer Relationship Management (CRM) structure with agribusinesses across 15 countries/value chains | 129/AUDA/OCEO/GROW/CQS/2020 | OCEO | AfDB/MS | CQS |  | 40000 |  | CEO | 2020-06-25 |  | 2020-06-30 |  | 2020-07-03 |  | 2020-07-17 |  | 2020-07-31 |  | 2020-08-14 |  | 2020-08-17 |  | 2020-08-31 |  | n/a | n/a | n/a | n/a | n/a | n/a | 2020-09-28 |  | 2020-09-14 |  | 2020-10-01 |  | 2020-10-06 |  |  | 2020-10-08 |  | 2020-10-15 |  |  |  |  | n/a | n/a | 2020-10-29
| GRAND TOTAL |  |  |  |  | 7002000
Formulas:
TOR Approval Date = [Preparation Term of Reference]+5
Advertise REOI on website = [TOR Approval Date]+3
Lead-time before Shortlist = [Advertise REOI on website]+14
Submission Evaluation Report (T) = [Lead-time before Shortlist]+14
Submission Evaluation Report (T) = [Submission / Opening Date]+14
Plan = [Negotiation (N)]+5
Plan = [Opening Financial Proposals]+14
Negotiation (N) = [Submission Evaluation Report (T)]+5
Negotiation (N) = [Opening Financial Proposals]+5
Draft Contract Vetting = [Plan]+3
No-objection Date = [Draft Contract Vetting]+5
No-objection Date = [Short List]+14
Contract Award = [No-objection Date]+2
Contract Signature = [Contract Award]+7
Draft Report / Commencement = [Contract Signature]+14
Short List = [Lead-time before Shortlist]+14
Request for Proposals / Bid = [No-objection Date]+3
Request for Proposals / Bid = [TOR Approval Date]+3
Submission / Opening Date = [Request for Proposals / Bid]+30
No Objection evaluation Report (T) = [Submission Evaluation Report (T)]+14
Opening Financial Proposals = [No Objection evaluation Report (T)]+7
APPROVED - MEMO ON FILE
Note on C25: Batho Maruping: in conjunction with OCEO
Note on C28: Batho Maruping: in conjunction with OCEO
Note on C30: Batho Maruping: in conjunction with OCEO
Note on C67: Batho Maruping: in conjunction with DPDC
Note on C68: Batho Maruping: in conjunction with KMPE
Note on C70: Batho Maruping: in conjunction with OCEO
Note on C78: Batho Maruping: in conjunction with OCEO

## Goods & Non-Consulting Services
[9 empty] | Specifications |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Goods contract Procurement Description* and Non-Consultancy Services | Reference Number | Department | Source of Funding | Estimated Amount in US $ | Actual Amount in US $ | Procurement Method | Pre-or Post Qualification | Approval Authority | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$'000 | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Procurement of hardware for setting up national helpdesks and installation of land data portals | 1/AUDA/DPDC/ENV/RFB/2020 | DPDC | MS | 150000 |  | RFB | Post | IPC-AU | 2020-07-01
Procurement and Installation of servers in 10 Countries | 2/AUDA/DPDC/ENV/RFQ/2021 | DPDC | MS | 20000 |  | RFQ | Post | CEO | 2020-07-02
Procurement and installation of software for e-procurement system | 3/AUDA/DO/PROC/RFQ/2020 | DO | MS | 100000 |  | RFQ | Post | IPC-AUDA-NEPAD | 2020-07-03
Procurement and installation of software for procure-to-pay system | 4/AUDA/DO/PROC/RFQ/2020 | DO | MS | 100000 |  | RFQ | Post | IPC-AUDA-NEPAD | 2020-07-04
Procurement of office cabinets | 5/AUDA/DO/FIN/RFQ/2020 | DO | MS | 11000 |  | RFQ | Post | Head of Procurement | 2020-07-05
Procurement of a software licence & training of staff for automated archiving system | 6/AUDA/DO/FIN/RFQ/2020 | DO | MS | 40000 |  | RFQ | Post | CEO | 2020-07-06
Procurement of office cabinets for record keeping | 7/AUDA/DO/HR/RFQ/2020 | DO | MS | 14000 |  | RFQ | Post | Head of Procurement | 2020-07-07
Procurement of Furnitures & Fixtures | 8/AUDA/DO/ADMIN/RFQ/2020 | DO | MS | 33750 |  | RFQ | Post | CEO | 2020-07-08
Procurement and Installation of of IT Equipment for Burkina Faso and Senegal Offices (Phones, VC, LAN) | 9/AUDA/DO/MIS/RFQ/2020 | DO | MS | 25000 |  | RFQ | Post | CEO | 2020-07-09
Procurement and Installation of Datacenter Infrastructure | 10/AUDA/DO/MIS/RFQ/2020 | DO | MS | 22000 |  | RFQ | Post | CEO | 2020-07-10
Procurement and Installation of of IT Equipment (Voice, Video, Data) | 11/AUDA/DO/MIS/RFQ/2020 | DO | MS | 120000 |  | RFB | Post | IPC-AU | 2020-07-11
Hire an Event Organiser/Firm for the ACJ! 2020 Conference | 12/AUDA/HCID/SKI/RFQ/2020 | HCID | GIZ | 25000 |  | RFQ | Post | CEO | 2020-07-12
Events management company for convening plenary meetings/work sessions for Grow Africa AfDB Project | 13/AUDA/OCEO/GROW/RFQ/2020 | OCEO | AfDB | 60000 |  | RFQ | Post | IPC-AUDA-NEPAD | 2020-07-13
Procurement of Partnership branding materials (bags, customised paper folders, etc) | 14/AUDA/DTCPF/TCP/RFQ/2020 | DTCPF | MS | 8000 |  | RFQ | Post | Head of Procurement | 2020-07-14
APET/CJED promotional materials | 15/AUDA/DTCPF/TCP/RFQ/2020 | DTCPF | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procument of services for the production of the AUDA-NEPAD profiling video “Towards The Africa we Want” | 16/AUDA/DTCPF/SID/RFQ/2020 | DTCPF | MS | 30000 |  | RFQ | Post | CEO | 2020-06-02
Procurement of mobile telephones, data, airtime and accessories for AUDA-NEPAD | 17/AUDA/DO/ADMIN/RFQ/2020 | DO | MS | 100000 |  | RFQ | Post | IPC-AUDA-NEPAD | 2020-06-03
Procurement of various publications - Design, layout, printing and translation | 18/AUDA/KMPE/ED/RFQ/2020 | KMPE | MS | 90000 |  | RFQ | Post | IPC | 2020-06-04
Procurement of various Translation, Editing and design of the portal | 19/AUDA/KMPE/KMD/RFQ/2020 | KMPE | MS | 90000 |  | RFQ | Post | IPC | 2020-06-05
Procurement of various translation,editing and printing of knowledge products for AUDA-NEPAD | 20/AUDA/KMPE/KMD/RFQ/2020 | KMPE | MS | 110000 |  | RFQ | Post | IPC-AUC | 2020-06-06
Procurement of training and licence for knowledge certificate | 21/AUDA/KMPE/KMD/RFQ/2020 | KMPE | MS | 20000 |  | RFQ | Post | CEO | 2020-06-07
Procurement of design and KM trainings | 22/AUDA/KMPE/KMD/RFQ/2020 | KMPE | MS | 30000 |  | RFQ | Post | CEO | 2020-06-08
Procurement of software & licences for KM | 23/AUDA/KMPE/KMD/RFQ/2020 | KMPE | MS | 30000 |  | RFQ | Post | CEO | 2020-06-09
Procurement office equipment for centres of excellence | 24/AUDA/KMPE/CE/RFB/2020 | KMPE | MS | 300000 |  | RFB | Post | IPC-AUC | 2020-06-10
Procurement of translation,editing and printing of knowledge products for centres of excellence | 25/AUDA/KMPE/CE/RFQ/2020 | KMPE | MS | 63000 |  | RFQ | Post | IPC-AUDA-NEPAD | 2020-06-11
Procurement of cleaning services for AUDA-NEPAD offices in Midrand South Africa | 26/AUDA/DO/ADMIN/RFB/2020 | DO | MS | 85000 |  | RFB | Post | IPC-AUDA-NEPAD | 2020-04-10
Procurement of ArcGIS Enterprise Software (COVID related) | 27/AUDA/DPDC/ENV/DP/2020 | DPDC | MS | 33235 |  | DP | Post | CEO | 2020-05-15
Procurement and installation of Data Server to strengthen Health Data Systems in Burkina Faso | 28/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Cameroon | 29/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Egypt | 30/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Eswatini | 31/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Ethiopia | 32/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Ghana | 33/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Mozambique | 34/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Senegal | 35/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Uganda | 36/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Procurement and installation of Data Server to strengthen Health Data Systems in Zimbabwe | 37/AUDA/PIPD/DAR/RFQ/2020 | PIPD | MS | 25000 |  | RFQ | Post | CEO | 2020-07-15
Software licences - Adobe License (6500)Meltwater Media Tracking (7000) | 38/AUDA/OCEO/COM/RFQ/2020 | OCEO, Comms | MS | 13500 |  | RFQ | Post | Head of Procurement | 2020-07-16
Media banners & standard banners on new logo | 39/AUDA/OCEO/COM/RFQ/2020 | OCEO, Comms | MS | 5000 |  | RFQ | Post | Head of Procurement | 2020-07-17
Support annual programmatic activties - materials and consultancy | 40/AUDA/OCEO/CEO/RFQ/2020 | OCEO | MS | 10000 |  | RFQ | Post | Head of Procurement | 2020-07-18
Internal Policy Coherance - publications and writers | 41/AUDA/OCEO/CEO/RFQ/2020 | OCEO | MS | 5000 |  | RFQ | Post | Head of Procurement | 2020-07-19
Office Stationary / Equipment / Hardware / Software for OCEO | 42/AUDA/OCEO/CEO/RFQ/2020 | OCEO | MS | 5000 |  | RFQ | Post | Head of Procurement | 2020-07-20
Publiciation of Offical reports (Procure professional thematic report and CEOs hand over report) | 43/AUDA/OCEO/CEO/RFQ/2020 | OCEO | MS | 30000 |  | RFQ | Post | CEO | 2020-07-21
Support to OCEO for Legal services | 44/AUDA/OCEO/LEG/RFQ/2020 | OCEO, Legal | MS | 50000 |  | RFQ | Post | CEO | 2020-07-22
Procure the rights to access and host the TMS - Truck Monitoring System tool | 45/AUDA/OCEO/MOV/RFQ/2020 | OCEO - MoveAfrica | MS | 50000 |  | DP | Post | CEO | 2020-07-23
Consultancy to the private sector unit priorities | 46/AUDA/OCEO/MOV/RFQ/2020 | OCEO - MoveAfrica | MS | 35000 |  | RFQ | Post | CEO | 2020-07-24
MoveAfrica Portal | 47/AUDA/OCEO/MOV/RFQ/2020 | OCEO - MoveAfrica | MS | 20000 |  | RFQ | Post | CEO | 2020-07-25
Support to private sector unit reports | 48/AUDA/OCEO/MOV/RFQ/2020 | OCEO - MoveAfrica | MS | 20000 |  | RFQ | Post | CEO | 2020-07-26
Whiteboard documentary | 49/AUDA/OCEO/MOV/RFQ/2020 | OCEO - MoveAfrica | MS | 20000 |  | RFQ | Post | CEO | 2020-07-27
Management of AUDA-NEPAD governance architecture | 50/AUDA/OCEO/PRO/RFQ/2020 | OCEO, Protocol | MS | 80000 |  | RFB | Post | IPC-AUDA-NEPAD | 2020-07-28
Design and printing of operational strategy for implementation of blueprint on Rural Transformation | 51/AUDA/PIPD/RUR/RFQ/2020 | PIPD | MS | 10000 |  | RFQ | Post | Head of Procurement | 2020-07-29
printing of Post-COVID report to support Member states recovery on Tourism (incl. Translation & Proof reading) | 52/AUDA/PIPD/RUR/RFQ/2020 | PIPD | DP | 20000 |  | RFQ | Post | CEO | 2020-07-30
printing of the 3rd Edition of the Rural Futures Atlas | 53/AUDA/PIPD/RUR/RFQ/2020 | PIPD | DP | 20000 |  | RFQ | Post | CEO | 2020-07-31
Purchase Office Equipment and Communications Materials | 54/AUDA/PIPD/RUR/RFQ/2020 | PIPD | DP | 50000 |  | RFQ | Post | CEO | 2020-08-01
|  | GRAND TOTAL |  | 2428485
APPROVED - MEMO ON FILE
Note on E40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to be bought by IT

## Works
[10 empty] | Specifications |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Goods contract Procurement Description* | Reference Number | Department | Source of Funding | Estimated Amount in US $ | Actual Amount in US $ | Variance | Procurement Method | Pre-or Post Qualification | Approval Authority | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$'000 | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Procurement of Engineering procurement contractor for Nyadire/Zimbabwe Minigrid (COVID related) - cancelled | 1/AUDA/DPDC/ENV/RFB/W/2020 | DPDC | MS |  |  |  | RFB | Post | AUDA IPC | 2020-05-01 | 2020-05-02 | 2020-05-11 | 2020-05-11
Procurement of Engineering procurement contractor for Niger Minigrid (COVID related) | 2/AUDA/DPDC/ENV/RFB/W/2020 | DPDC | MS | 67000 |  |  | RFB | Post | AUDA IPC | 2020-05-01 | 2020-05-02 | 2020-05-11 | 2020-05-11
Procurement of Engineering procurement contractor for Sierra Leone Minigrid (COVID related) | 3/AUDA/DPDC/ENV/RFB/W/2020 | DPDC | MS | 67000 |  |  | RFB | Post | AUDA IPC | 2020-05-01 | 2020-05-02 | 2020-05-11 | 2020-05-11
Procurement of Engineering procurement contractor for Soti Source/Zimbabwe Minigrid (COVID related) | 4/AUDA/DPDC/ENV/RFB/W/2020 | DPDC | MS | 67000 |  |  | RFB | Pre | AUC -IPC | 2020-07-02
Procurement of Engineering procurement contractor for Malawi Minigrid | 5/AUDA/DPDC/ENV/RFB/W/2020 | DPDC | MS | 325000 |  |  | RFB | Pre | AUC -IPC | 2020-07-03
|  | GRAND TOTAL |  | 526000
Formulas:
Bidding Period = [Spec Proc Notice Advert]
APPROVED - MEMO ON FILE

## Data
Type of Procurement | Department | Funding | Method | Type | P/Post | Approval Authority
Consultancy | OCEO | PIDA CAP/CCTTFA | QCBS | Lumpsum | Prior | Head of Procurement/Director
Works | DO | AfDB PIDA CAP | CQS | Time-Based | Post | CEO
Goods | DTCPF | AfDB/MS | ICS (with advert) |  |  | IPC - AUDA-NEPAD
Non Consulatancy | DPDC | Core | SSS |  |  | IPC - AUC
| DPIP | Spanish Fund | QBS |  |  | Tender Board
| DKMPE | LandGov | ICS
|  | World Bank | LCS
|  | MSC | FBS
|  | China Aid | RFQ
|  | WB | LB
|  | BMGF | Open Tender
|  | Global Fund | CQC
|  | AGRA | ICS (without advert)
|  | MS | RFB
|  | UEMOA | DP
KFW
NORAD
AFD
GIZ